## Status
STATUS | NO. OF TICKETS
Open | 15
Assigned | 39
Close | 47
Forwarded | 9
Inforequired | 13
Not assigned | 29
Resolve | 96
Total tickets | 248

## 02 Aug
SL. No. | Ticket No. | Date Raised on | Priority | Raised By | Ticket Description | Action Owner | Current Status
1 | 438 | 2017-05-08 10:55 | HIGH | Nitin Kumar Gupta | Period 2 2017 is not open. Kindly open the same. | SAP FINANCE | Close
2 | 448 | 2017-05-08 13:04 | HIGH | Nagsen Ambadas Wankhede | Dear Wipro team FLM file view access is to everyone right now means only concerned people should see the details in file not the one who access to FLM. Could you please look into this urgently. Kind regards Nagsen | SAP FLM | Resolve
3 | 456 | 2017-05-09 13:42 | HIGH | Nagsen Ambadas Wankhede | Dear Team I had a raised a travel request for which no intimation from workflow been gone to my manager. and on ESS if I am trying to change it shows Travel/Expense request already open. Could you please check and let me know the resolution. Kind Regards Nagsen | SAP ESS | Close
4 | 458 | 2017-05-09 16:59 | HIGH | PRIYANKA KUMARI | My file management menu are not add please add. | SAP FLM | Resolve
5 | 459 | 2017-05-10 13:54 | HIGH | Nitin Kumar Gupta | Missing authorization as per attachement | SAP FINANCE | Close
6 | 461 | 2017-05-11 10:12 | HIGH | SAMEER KUMAR | Please provide the password, as I am not able to login. | SAP ESS | Resolve
7 | 464 | 2017-05-11 12:51 | HIGH | NIRANJAN KUMAR | Dear Team, When accessing the "Employee Search" into ESS portal then following error occurs "Critical Error A critical error has occured. Processing of the service was terminated. Unsaved data has been lost. Contact your system administrator." | SAP ESS | Close
8 | 465 | 2017-05-11 12:58 | HIGH | DHARMENDRA KUMAR | I am not able to see the current status of file (EESL/IT/Printers Colour/2017/8) which was created by me earlier. Kindly do the needful. | SAP FLM | Close
9 | 466 | 2017-05-11 15:35 | HIGH | Nagsen Ambadas Wankhede | Dear Team When I submitted the travel expense for for save as draft and then clicked on Display Expense form I am getting below error. Kindly Resolve this ASAP Error at end of form processing Error SOAP Framework error: SOAP Runtime Exception: CSoapExceptionTransport : HTTP receive failed with exception communication_failure (100,101). | SAP ESS | Close
10 | 467 | 2017-05-11 15:41 | HIGH | Nagsen Ambadas Wankhede | Dear Team When I submitted the travel expense Getting a SAP backend screen can you please check this? | Not Assigned | Close
11 | 468 | 2017-05-12 10:53 | HIGH | Nitin Kumar Gupta | Payment program is not picking the correct bank account. instead of icici bank 1803, it picking UTI bank. Kindly correct the same. | SAP FINANCE | Close
12 | 469 | 2017-05-12 10:56 | HIGH | Vikash Kumar Gupta | My SAP ESS Portal not open.kindly solve the problem. what is my User ID and password of SAP ESS portal. | SAP ESS | Resolve
13 | 470 | 2017-05-12 11:20 | HIGH | ARVIND SINGH BHANDARI | I am unable to login. Kindly reset my password and send me the details | SAP ESS | Resolve
14 | 474 | 2017-05-12 12:04 | HIGH | MAYANK GAUR | Dear Team, I am getting Mobile Bill Reimb. Request as soon as anyone submit the bill. I am not the concern person regarding this. Please check. | SAP ESS | Resolve
15 | 476 | 2017-05-12 15:01 | HIGH | Nitin Kumar Gupta | authorization issue in tcode PA20 ( screenshot attached) | SAP FINANCE | Close
16 | 480 | 2017-05-13 08:29 | HIGH | Madhurya Mahanta | Sir/Madam, While declaring IT projection, I have entered in three of the followings under 80c: 1. LIC 2. NSC VII 3. Term deposit under 80C but now its showing in different line. Also declared under house rent, which is also missing from my IT declaration. I have got acknowledgements from finance team for approval of both the projections (80C and house rent) Kindly look into the matter, as I have received less salary for the month of April 2017. | SAP ESS | Resolve
17 | 490 | 2017-05-15 13:01 | HIGH | Nitin Kumar Gupta | Kindly check attachment for Details | SAP FLM | Resolve
18 | 494 | 2017-05-16 11:41 | MEDIUM | POLASH DAS | Unable to create Travel Request through ESS portal. Error message attached | SAP ESS | Resolve
19 | 498 | 2017-05-16 16:28 | HIGH | ANIMESH AGARWAL | I ( Animesh Agarwal) have not able to access the SAP portal with user id 20000044 and default password is Hello123. Kindly look up the issue | SAP ESS | Resolve
20 | 499 | 2017-05-16 17:53 | HIGH | VINAYAK GOYAL | When i created tour approval i did not check on travel mode. In that case my request has been submitted for approval. It should be mandatory field. Kindly look this matter and resolve it as soon as possible. | SAP ESS | Resolve
21 | 500 | 2017-05-16 17:57 | HIGH | VINAYAK GOYAL | When i am creating expenses against tour i am not able to create claim because there is no bus option in drop down. Kindly add bus option in drop down. | SAP ESS | Close
22 | 501 | 2017-05-16 18:07 | HIGH | VINAYAK GOYAL | In tour approval there is no option for cab approval on tour because i am not eligible for cab. This option should be present there as optional. Kindly look into this matter. | SAP ESS | Resolve
23 | 504 | 2017-05-17 11:22 | HIGH | RAHUL SHARMA | Dear SAP Team, I am trying to raise the request in context of Laptop reimbursement, but the portal is showing en error while submission. Kindly resolve. Screenshot is being attached for reference. Error at the top of window. | SAP ESS | Resolve
24 | 509 | 2017-05-17 15:35 | HIGH | Shubramoy Sengupta | eesl portal not functioning my SAP ID 30000008 password Eesl@123 Till now it's not possible for me to enter eesl portal. | SAP ESS | Resolve
25 | 510 | 2017-05-17 18:22 | HIGH | Kavish Agarwal | Request to kindly update the DA as per latest circular Attaching the expense report and latest circular available with me. | SAP ESS | Resolve
26 | 513 | 2017-05-18 11:17 | HIGH | AVNEESH KUMAR VATS | Hello Team Unable to print OPD medical form getting below Error. Please check and fix the same , Intimate once done Print version Communication Failure: RFC destination SALV_WD_EXPORT_PDF does not exist. - Display Help Display Message Log | SAP ESS | Resolve
27 | 514 | 2017-05-18 12:10 | HIGH | TOSH AGRAWAL | I have forgotten my password. Kindly reset the password and share the new one. Thanks. | Not Assigned | Close
28 | 520 | 2017-05-19 11:50 | HIGH | ARVIND SINGH BHANDARI | Dear Team, I am unable to login at http://essportal.eesl.co.in/irj/portal, Kindly reset my password. | SAP ESS | Resolve
29 | 529 | 2017-05-22 12:29 | HIGH | Nitin Kumar Gupta | Dear sir Accounting entries of claim from ESS portal is not coming correct. Currently is coming as Exp Dr & Exp payable Cr. Need to be corrected as Exp Dr & Employee Vendor Cr. Thanks | SAP FINANCE | Close
30 | 530 | 2017-05-22 12:39 | HIGH | Nitin Kumar Gupta | Dear sir Accounting entries of claim from ESS portal is not coming correct. Currently is coming as Exp Dr & Exp payable Cr. Need to be corrected as Exp Dr & Employee Vendor Cr. Thanks | SAP FINANCE | Close
31 | 531 | 2017-05-22 12:41 | HIGH | Nitin Kumar Gupta | Dear sir For Trip no 10000002, DA is calculated as Rs 3000 instead of Rs 2400. Request you to kindly correct the same. Thanks | SAP PAYROLL And HCM | Resolve
32 | 532 | 2017-05-22 12:41 | HIGH | Nitin Kumar Gupta | Dear sir For Trip no 10000003, DA is calculated as Rs 2250 instead of Rs 1800. Request you to kindly correct the same. Thanks | SAP PAYROLL And HCM | Resolve
33 | 534 | 2017-05-22 14:27 | HIGH | DHARMENDRA KUMAR | A file was created (EESL/IT/TABLETS) with workflow Mayank Gaur--Avaneesh Vats-- Sudeep Bhar/Mohit Khatri (Parallel) --SHANKAR GOPAL--Saurabh Kumar. 1. But, after approval from Sudeep Bhar, it is showing that file was moved to Ashok Kumar Arora. However, file has not reached to in tray of Ashok Kumar Arora. 2. After approval of MOHIT KHATRI, file has moved to Mayank Gaur instead of SHANKAR GOPAL. Kindly look into the matter and resolve at the earliest. | SAP FLM | Resolve
34 | 537 | 2017-05-23 10:30 | HIGH | RAHUL TIWARI | How to Take LTC exemption through ESS Portal. | SAP PAYROLL And HCM | Resolve
35 | 538 | 2017-05-23 11:05 | HIGH | Santosh Kumar | My Name is SANTOSH KUMAR My SAP ID is 30000017 but in SAP Profile My Name show Santhosh Kumar instead of SANTOSH KUMAR. I have already mail to concern person but there is no update till date kindly update my profile as soon as possible. | SAP ESS | Resolve
36 | 540 | 2017-05-23 11:50 | HIGH | Nitin Kumar Gupta | Kindly add Following fields in employee salary slip. 1. Date of Joining (EESL) 2. Date of Joining (current Grade) 3. Designation 4. Bank A/c number 5. (currently last 3 digit not coming) 6. PF number 7. EESL Logo | SAP PAYROLL And HCM | Open
37 | 542 | 2017-05-23 17:46 | HIGH | MAYANK GAUR | Dear Team, As per my previous Ticket No. 737, I am getting Mobile Bill Reimb. Request as soon as anyone submit the bill. I am not the concern person regarding this. Please check. Attachment | SAP ESS | Resolve
38 | 543 | 2017-05-23 18:39 | HIGH | Gourav Roy | Declaration not accepted even after filling all details. Bill/Invoices not required for employees while declaring under Company Leased Accomation | SAP ESS | Close
39 | 545 | 2017-05-24 11:55 | HIGH | Heena Chwala | please provide the tcode authorization | SAP FINANCE | Close
40 | 546 | 2017-05-24 12:12 | HIGH | ARVIND SINGH BHANDARI | please reset the password of ess portal | SAP ESS | Resolve
41 | 547 | 2017-05-24 12:20 | HIGH | SHAMSHAD UDDIN | Forgot the Password, pls generate the new one asap. My SAP CODE - 20000133 | SAP ESS | Resolve
42 | 548 | 2017-05-24 13:48 | HIGH | Gourav Roy | Maximum Loan amount eligibility is Rs.89445/-. System is approving Rs.222613/-. | SAP ESS | Resolve
43 | 550 | 2017-05-24 15:03 | HIGH | NIRANJAN KUMAR | When I login, it prompts me to change password, though I already changed the default password. When I change the password it says "Incorrect old password." The same password is working on the initial screen. Plz look into this. My SAP ID is 10000091 | SAP ESS | Close
44 | 553 | 2017-05-24 19:07 | MEDIUM | Nitin Kumar Gupta | Kindly install BI and BPC in my machine. | Not Assigned | Forwarded
45 | 555 | 2017-05-25 11:06 | HIGH | AVNEESH KUMAR VATS | Unable to create Tour request using Personal Car for travel. When using ESS screen unable to save request getting error This combination of vehicle type and vehicle class is not permitted | SAP ESS | Resolve
46 | 563 | 2017-05-26 10:40 | HIGH | Nitin Kumar Gupta | As discussed, in the payment file generated by SAP, there are some payment are coming as Zero amount instead of actual payment amount. Request you to kindly correct to same. | SAP FINANCE | Close
47 | 564 | 2017-05-26 15:31 | HIGH | Kavish Agarwal | I am on tour from 1st May to 4th May, but I am unable to claim on the SAP. Further to it, the DA (E-3 Grade) which is self calculated is wrong and need to be updated. Kindly send some one and also update the same at the earliest Thanks in advance | SAP ESS | Resolve
48 | 565 | 2017-05-26 15:34 | HIGH | Kavish Agarwal | I am on tour from 1st May to 4th May, but I am unable to claim on the SAP. Further to it, the DA (E-3 Grade) which is self calculated is wrong and need to be updated. Kindly send some one and also update the same at the earliest Thanks in advance | SAP ESS | Close
49 | 569 | 2017-05-26 17:09 | HIGH | Gourav Roy | Eligibility for Claims is showing 0 under claims and reimbursement. | SAP ESS | Close
50 | 570 | 2017-05-26 17:11 | HIGH | Heena Chwala | Please find attached list of voucher having following issue. 1. Debit amount Total is not coming correct. 2. Prepared by and Verified by is not coming. Request you to kindly correct the same on priority. ( for Details kindly refer attachment) Thanks | SAP FINANCE | Close
51 | 571 | 2017-05-26 17:13 | HIGH | Heena Chwala | Please find attached list of voucher having following issue. 1. Debit amount Total is not coming correct. 2. Prepared by and Verified by is not coming. Request you to kindly correct the same on priority. ( for Details kindly refer attachment) Thanks | SAP FINANCE | Close
52 | 572 | 2017-05-26 17:13 | HIGH | Heena Chwala | Please find attached list of voucher having following issue. 1. Debit amount Total is not coming correct. 2. Prepared by and Verified by is not coming. Request you to kindly correct the same on priority. ( for Details kindly refer attachment) Thanks | SAP FINANCE | Close
53 | 575 | 2017-05-29 10:42 | HIGH | Nitin Kumar Gupta | Dear Sir Finance Deptt. want to see the trial balance for the period of May 1, 2017 to May 15, 2017. Request you to kindly provide the tcode and authorization for the same. Thanks & Best Regards | SAP FINANCE | Open
54 | 576 | 2017-05-29 10:57 | HIGH | NIKHIL BHANDARI | Recently created IT Declaration vide 1000013600006 through ESS. However, the same is not showing in the Income Tax Projection. Attached herewith is proof of IT Declaration Submitted. | SAP ESS | Assigned
55 | 577 | 2017-05-29 11:54 | HIGH | AJAY RAJ | Is there a specific limitation on the file size that we can upload on SAP as attachment as I am seeing files being rejected. Can the limit be specified on SAP when user enters the detail (I think it is 300kb) | SAP ESS | Resolve
56 | 585 | 2017-05-30 10:58 | HIGH | NEHA GERA | Expense report is not being sent for approval. Please look into the matter. | SAP ESS | Resolve
57 | 587 | 2017-05-30 11:39 | HIGH | JISHA JYOTI | Dear Vivek Sir, As I was claiming my mobile bill,claim month & bill period is not matching which is not allowing me further to claim. Kindly do the needful. | SAP ESS | Close
58 | 593 | 2017-05-31 11:29 | HIGH | NIKHIL BHANDARI | On follow up with Finance, IT Declaration put up against Income from Other sources was not considered for tax deduction. Request was made vide declaration no. 1000013600006 on 25/05/2017 along with other declaration. Snapshot attached. | SAP ESS | Open
59 | 601 | 2017-06-01 05:18 | HIGH | Nitin Kumar Gupta | please incorporate the Claim details as well in the payment advice generated from SAP ( kindly see attachment for details ) | SAP PAYROLL And HCM | Open
60 | 605 | 2017-06-01 11:39 | MEDIUM | MAYURI CHAUKHANDE | Installation of SAP on the system | SAP ESS | Resolve
61 | 607 | 2017-06-01 16:02 | HIGH | NIKHIL BHANDARI | Mobile Bill Reimbursement Error. As confirmed in HR Request not Received. On edit while reviewing it is showing error "Already in process in approval". | SAP ESS | Forwarded
62 | 608 | 2017-06-01 17:38 | HIGH | JISHA JYOTI | Dear Vivek Sir, I am unable to edit my mobile bills which were saved successfully in drafts.Please help. Regards, Jisha Nair. | SAP ESS | Close
63 | 609 | 2017-06-01 17:46 | HIGH | Deepak Hansda | My Login password is locked for SAP portal. | SAP ESS | Close
64 | 610 | 2017-06-01 17:48 | HIGH | Karmbir | Unable to book claims through SAP. Enclosed is the Error sheet. Please take urgent action. | SAP ESS | InfoRequired
65 | 611 | 2017-06-01 22:36 | HIGH | TOSH AGRAWAL | When filing tour claims, if the Receipt Date is before the travel time, it is showing an error. The logo next to claim type turns yellow instead of green. In the tour claim I am trying to submit, the receipt date of the air tickets and hotel bookings are before the travel time. It was booked in advance before commencing the tour. | SAP ESS | Close
66 | 612 | 2017-06-01 22:37 | HIGH | TOSH AGRAWAL | When filing tour claims, wherever receipt is not available, such as Cab Domestic without bill or Auto Rickshaw D., what is to be written in the receipt date column as there is no option to leave the column blank. | SAP ESS | Close
67 | 613 | 2017-06-01 22:38 | HIGH | TOSH AGRAWAL | While filing tour claims, calculation of 'Meals per Diem' is showing wrong calculation e.g. DA for 1.5 days of principal city is showing amount equivalent to 1 day. It is not taking for 0.5 days. In particular case the undersigned left Delhi at 14:23 on 20/05/2017 and reached Varanasi (principal city) and stayed overnight. Then, the City was left at 11:00 on 21/05/2017 for further journey to Ambikapur (ordinary city). In this case, as per rules of EESL, DA for 1.5 days of stay at principal city is applicable. Nevertheless, the system is calculating Meals per Diem for 0.5 day less for the whole tour duration i.e. total tour duration in this case is 5.5 days but it is showing for 5 days. It seems the system is calculating per diem on the basis of time duration in the particular city and not as per the rules and policy of EESL which is for clock day. Kindly get it rectified and intimate upon rectification so that tour claim can be sent for approval. | SAP ESS | Resolve
68 | 623 | 2017-06-02 14:31 | HIGH | Megha Tyagi | i’m unable to login into my SAP-EES portal. My EES portal detail is mentioned below for your kind reference: Username- 10000107 Request you to please reset my password. Thanks & Regards, Sannivesh Gupta Engineer Energy Efficiency Services Limited | SAP ESS | Resolve
69 | 624 | 2017-06-02 15:03 | HIGH | SANNIVESH KUMAR GUPTA | Please reset my SAP-ESS portal password as i'm unable to login. Username-10000107 | SAP ESS | Resolve
70 | 626 | 2017-06-02 16:17 | HIGH | Mani Kumar Thakur | My SAP ESS portal doesn't open with my SAP ID & Password. Kindly rectify else suggest some alternate options. My SAP ID is 30000040. | SAP ESS | Resolve
71 | 627 | 2017-06-02 16:39 | HIGH | MUKESH KUMAR RAY | claim and reimbursement is not working. | SAP ESS | Resolve
72 | 630 | 2017-06-03 17:28 | HIGH | RAHUL TIWARI | Interest on HBA i.r.o of Sharat Chandra and Dharmendra Kumar (Officer IT), there is no accounting treatment for Interest in SAP as well as their perks. Kindly look into it. | SAP PAYROLL And HCM | Resolve
73 | 631 | 2017-06-03 17:28 | HIGH | RAHUL TIWARI | Interest on HBA i.r.o of Sharat Chandra and Dharmendra Kumar (Officer IT), there is no accounting treatment for Interest in SAP as well as their perks. Kindly look into it. | SAP PAYROLL And HCM | Resolve
74 | 632 | 2017-06-03 17:29 | HIGH | RAHUL TIWARI | Interest on car loan i.r.o Kumar Saurabh (10000004) has not been calculated in SAP, Also no Accounting treatment for the same has been done in SAP. | SAP PAYROLL And HCM | Resolve
75 | 634 | 2017-06-05 09:19 | HIGH | Nitin Kumar Gupta | Dear Kamran /Ashish Mail id is not maintained in my SAP user id profile. Due to this, whenever I am making the payment, email advice getting failed. Request you to kindly maintain it as “rkishore@eesl.co.in” | SAP FINANCE | Close
76 | 636 | 2017-06-05 10:38 | HIGH | Sakshi Jindal | I had created zero advance travel request with Trip id 10000088 few days back which has been approved by R.O. The same can be viewed through 'Travel expense report' link in my ESS account as shown in the attached image file. However, no trip id is shown under 'Travel work center' (as shown in the attached image) due to which i am not able to create Travel Expense report. My employee id is 20000136. Kindly look into the matter and resolve. | SAP ESS | Resolve
77 | 640 | 2017-06-05 11:28 | HIGH | Kishor Gopichand Chavan | I have submitted IT declaration through SAP in the month of April, 2017. I have declared as under: Childern Tution fees Home loan Principle amount payble in 2017-18 Home loan Interest amount staying in rented Home so Rent amount My own house is also leased for rent that also i have declared. However, in Tax calculation on CPF amount has been considered for salary for the Month of April amd May, 2017, which ended with Tax deduction on higher side. It is requested to do needful correction in the Month of June, 2017 Salary calculations | SAP PAYROLL And HCM | Assigned
78 | 647 | 2017-06-05 14:54 | HIGH | Amit Kumar Bhardwaj | I am not able to see / review Mr. Arvind Singh Bhandari's KRA / Appraisal document. The approval tab is missing. | SAP ESS | Close
79 | 649 | 2017-06-05 17:03 | HIGH | Satyam Gupta | Unable to login on SAP ESS Portal | SAP ESS | Resolve
80 | 650 | 2017-06-05 17:32 | HIGH | NIKITA SAXENA | User id: 20000055 Kindly unlock my password for ess portal. | SAP ESS | Resolve
81 | 651 | 2017-06-05 17:32 | HIGH | NIKITA SAXENA | User id: 20000055 Kindly unlock my password for ess portal. | SAP ESS | Resolve
82 | 652 | 2017-06-05 17:46 | HIGH | ARPIT GOEL | I have process payment through SAP but after process the payment some employees shows with zero value. | SAP FINANCE | Close
83 | 653 | 2017-06-05 17:49 | HIGH | ARPIT GOEL | I want to seen all entries which I have processed in SAP from 1april 2017 to till date in details but still not possible. | SAP FINANCE | Close
84 | 654 | 2017-06-06 09:42 | HIGH | ARPIT GOEL | BG warning message at the time of calculation of BG charges (BG Charges Validation) not working | SAP FINANCE | Open
85 | 655 | 2017-06-06 09:42 | HIGH | ARPIT GOEL | Except ICICI other bank host to host not working | SAP FINANCE | Open
86 | 656 | 2017-06-06 09:43 | HIGH | ARPIT GOEL | BG MIS report in detail with banking & party name rather than coding | SAP FINANCE | Open
87 | 657 | 2017-06-06 09:43 | HIGH | ARPIT GOEL | FD Report with Interest and TDS Bank Wise with banking & party name rather than coding | SAP FINANCE | Open
88 | 658 | 2017-06-06 09:43 | HIGH | ARPIT GOEL | Multiple Time One FD break (Calculation wrongly shown in SAP) | SAP FINANCE | Open
89 | 659 | 2017-06-06 11:09 | HIGH | RAHUL TIWARI | 1 PF Report generated is not correct. | SAP PAYROLL And HCM | Resolve
90 | 660 | 2017-06-06 11:10 | HIGH | RAHUL TIWARI | Admin charges on PF on wrongly calculated. | SAP PAYROLL And HCM | Resolve
91 | 661 | 2017-06-06 11:10 | HIGH | RAHUL TIWARI | Accounting treatment of interest on HBA is not there in SAP. | SAP PAYROLL And HCM | Resolve
92 | 662 | 2017-06-06 11:10 | HIGH | RAHUL TIWARI | Accounting treatment of interest on Conveyance Advance is not there in SAP. | SAP PAYROLL And HCM | Resolve
93 | 663 | 2017-06-06 11:10 | HIGH | RAHUL TIWARI | Employees Who absorbed as Regular, Exemption wrongly calculated. | SAP PAYROLL And HCM | InfoRequired
94 | 664 | 2017-06-06 11:10 | HIGH | RAHUL TIWARI | Most of the information are not cover in Pay Slip eg- UAN No., Designation, PF No., Company Name, PAN No. | SAP PAYROLL And HCM | Resolve
95 | 665 | 2017-06-06 11:11 | HIGH | RAHUL TIWARI | Bank File not generated | SAP PAYROLL And HCM | InfoRequired
96 | 668 | 2017-06-06 12:20 | HIGH | RITIKA BHANDARI | Furniture loan not developed in the system. Request had already been raised through email dated 12.05.2017. You are requested to create loan type as per the requirement | SAP ESS | InfoRequired
97 | 669 | 2017-06-06 12:23 | HIGH | RITIKA BHANDARI | You are requested to please include spectacles eligibility limit of Rs. 5000/- under OPD and rename the OPD reimbursement as "OPD reimb (incl. of spec. reimb. max upto Rs.5000/-) and remove the eligibility maintained separately for spectacles reimbursement. Request through email dated 05.06.2017 has already been raised. | SAP PAYROLL And HCM | Resolve
98 | 670 | 2017-06-06 12:28 | HIGH | RITIKA BHANDARI | List of BUH and RMs for travel approval request. The list of BUH and RM along with the E6 and above employees have already been shared dated 25.05.2017. You are requested to please upload the approvers for travel and confirm. | SAP ESS | Resolve
99 | 671 | 2017-06-06 13:27 | HIGH | DARPAN MAGO | Concern: Tour claims section not working Dear sir/ madam, The undersigned had created tour requests on SAP portal in back date, while hard copy approvals were already taken for them prior to the tour. This was done to process the tour expenses. Post creation of these two travel approval requests, no details of them were found on the 'Traveler Work Center' for further processing of expenses. It may be brought to your notice that the undersigned is unable to process these two travel claims amounting to over Rs. 20,000/- from the past 4 days. I am further attaching the screenshot for your reference and perusal. Problem start date: June 1, 2017 Till: Continuing Requesting an early intervention to fix the issues for processing of travel expenses. Regards, Darpan Mago Officer, Public Relations EESL Phone: 8800795454 | SAP ESS | Resolve
100 | 673 | 2017-06-06 14:12 | HIGH | RITIKA BHANDARI | Payslip should have a text mentioned so that external parties can consider payslip as valid document (Like Logo, UAN number, text about authorized signature) | SAP PAYROLL And HCM | Resolve
101 | 674 | 2017-06-06 14:58 | HIGH | RITIKA BHANDARI | Data Card reimbursement is not in ESS portal. You are are requested to kindly create. | SAP PAYROLL And HCM | Resolve
102 | 675 | 2017-06-06 15:17 | HIGH | RITIKA BHANDARI | Blood Group information is not visible on ESS portal. You are requested to kindly make the blood group editable to employees. | SAP PAYROLL And HCM | Resolve
103 | 676 | 2017-06-06 15:22 | MEDIUM | Himanshu Raj Verma | Dear Sir, It is to inform your that my SAP Netweaver Portal Password not working pl. help me | Not Assigned | Forwarded
104 | 677 | 2017-06-06 15:49 | HIGH | AVNEESH KUMAR VATS | Hello Vivek Please check the issue as attached coming for the Personal Car Tour | SAP ESS | Resolve
105 | 678 | 2017-06-06 16:25 | HIGH | SOUMYA PRASAD GARNAIK | DA calculation is not happening as per my grade. kindly sort out the issue. | SAP ESS | Resolve
106 | 682 | 2017-06-06 17:02 | HIGH | RAHUL TIWARI | Kindly change the Symbolic Account of Following G/Ls:- From TO 30001021 Lease Rec (10%) 30001022 3RI Negative diff. rent & 10009661 employee Contribution 10009661 Ee PF Contribution Ee VPF Contribution 10009661 employee Contribution 10009663 Employer Contribution Pension Contribution 10009661 employee Contribution 10009665 Admin Charges Payable Kindly change the Symbolic Account of Following G/Ls:- From TO 30001021 Lease Rec (10%) 30001022 3RI Negative diff. rent & 10009661 employee Contribution 10009661 Ee PF Contribution Ee VPF Contribution 10009661 employee Contribution 10009663 Employer Contribution Pension Contribution 10009661 employee Contribution 10009665 Admin Charges Payable change of Symbolic Account In SAP | SAP PAYROLL And HCM | Resolve
107 | 684 | 2017-06-06 17:34 | HIGH | SHAMSHAD UDDIN | Dear Team, In my Salary Statement (ESS account) of May, 2017 is same as April, 2017. Pics attached for your reference. | SAP PAYROLL And HCM | Resolve
108 | 685 | 2017-06-06 18:45 | HIGH | RAHUL TIWARI | There are some medical bills of last year which we need to book in current year. As all these claims are taxable , so kindly let us know how to process these claims in SAP. Is there any way that we can process it through JV and take the taxation impact in salary without paying it from payroll / offcycle. | SAP FINANCE | Close
109 | 686 | 2017-06-06 18:46 | HIGH | RAHUL TIWARI | There are some medical bills of last year which we need to book in current year. As all these claims are taxable , so kindly let us know how to process these claims in SAP. Is there any way that we can process it through JV and take the taxation impact in salary without paying it from payroll / offcycle. | SAP PAYROLL And HCM | Forwarded
110 | 687 | 2017-06-06 19:27 | HIGH | RAHUL TIWARI | TDS report through zfi_tdsmis is not working. | SAP FINANCE | Close
111 | 688 | 2017-06-06 19:27 | HIGH | RAHUL TIWARI | Arrear on PF is not mention in standard PF Report. | SAP PAYROLL And HCM | Forwarded
112 | 689 | 2017-06-07 09:50 | HIGH | Megha Tyagi | Photo Uploaded are not visible on ESS - MEEP Team | SAP ESS | Resolve
113 | 690 | 2017-06-07 09:51 | HIGH | Megha Tyagi | Restricted holidays are not shown in different colour - MEEP Team | SAP ESS | Resolve
114 | 691 | 2017-06-07 09:54 | HIGH | Megha Tyagi | Recall or resend a reimbursement claim. If rejected or sent wrongly, option to employee should be available to recall / comment. If wrongly rejected by approver, employee should be able to resend the same claim. | SAP ESS | Resolve
115 | 692 | 2017-06-07 09:54 | HIGH | Megha Tyagi | Recall or resend a reimbursement claim. If rejected or sent wrongly, option to employee should be available to recall / comment. If wrongly rejected by approver, employee should be able to resend the same claim.- MEEP Team | SAP ESS | Resolve
116 | 693 | 2017-06-07 09:56 | HIGH | Megha Tyagi | Salary slip of May 2017 has salary slip of April 2017 and May 2017 both.- MEEP Team | SAP ESS | Resolve
117 | 694 | 2017-06-07 09:58 | HIGH | Megha Tyagi | Spelling / punctuation mistakes (such as Fair instead of Fare w.r.t. Bus claim in Travel Claim) in ESS to be rectified- MEEP Team | SAP ESS | Resolve
118 | 697 | 2017-06-07 10:40 | HIGH | NIKITA SAXENA | Please find the list of ‘File types’ to be added in FLM as mentioned under: 1. Financial sheet 2. Agreement 3. Petition 4. RfP 5. Inter Office Memo (IOM) 6. MoU | SAP FLM | Close
119 | 698 | 2017-06-07 10:40 | HIGH | NIKITA SAXENA | Please find the list of ‘File types’ to be added in FLM as mentioned under: 1. Financial sheet 2. Agreement 3. Petition 4. RfP 5. Inter Office Memo (IOM) 6. MoU | SAP FLM | Close
120 | 699 | 2017-06-07 10:40 | HIGH | NIKITA SAXENA | Please find the list of ‘File types’ to be added in FLM as mentioned under: 1. Financial sheet 2. Agreement 3. Petition 4. RfP 5. Inter Office Memo (IOM) 6. MoU | SAP FLM | Close
121 | 701 | 2017-06-07 12:48 | HIGH | Heena Chwala | Trip no. 10000029, DA amount = Rs. 960 but system calculated it Rs 1500. Plz check | SAP PAYROLL And HCM | Close
122 | 708 | 2017-06-07 17:55 | HIGH | Himanshu Raj Verma | It is to inform you that my SAP ESS Portal not working right now there are asking user ID and Password please resolve the problem. And provide the user ID and Password | SAP ESS | Resolve
123 | 716 | 2017-06-08 13:41 | HIGH | KUNAL SONI | I am unabel to view the form 16 in the portal, kindly help. | SAP PAYROLL And HCM | Close
124 | 717 | 2017-06-08 14:10 | HIGH | NIKITA SAXENA | Kindly give authorization for transaction code 'PHAP_create' for setting performance plan | SAP PAYROLL And HCM | Resolve
125 | 723 | 2017-06-08 18:47 | HIGH | ATUL | login- 10000188, I am unable to login Please do the need full at earliest. | SAP ESS | Resolve
126 | 724 | 2017-06-08 19:33 | HIGH | Rahul Singh | I saved my performance plan, but now I am not able to edit. Following message appears on the top, Appraisal document 'PERFORMANCE PLAN (2017-2018)' is locked by you" | SAP ESS | Resolve
127 | 727 | 2017-06-09 11:12 | HIGH | RAHUL DEV GAUTAM | Not able to login. Error: User Authentication Failed | SAP ESS | Resolve
128 | 731 | 2017-06-09 16:38 | HIGH | Nitin Kumar Gupta | One again, in the payment file generated by SAP, there are some payment are coming as Zero amount instead of actual payment amount. Request you to kindly correct to same. Please see screenshot attached. | SAP FINANCE | Close
129 | 732 | 2017-06-09 16:44 | HIGH | UTKARSH KUMAR | Can't login .Password locked. kindly resolve ASAP,as today is the last day to file PMS | SAP ESS | Resolve
130 | 734 | 2017-06-09 18:30 | HIGH | Lavnish Goyal | Dear Team, I visited Delhi for SAP training from 12th May to 22 May, 2017. Now when I am trying to claim my expenses for that trip I am not able to see that travel request no. in the Traveler work center link. The travel request no is Travel Request (0010000176). Attaching the snapshot of approval of Travel Request and also of the Travel work center. | SAP ESS | Resolve
131 | 735 | 2017-06-09 18:35 | HIGH | SHAMSHAD UDDIN | Dear Team, In my Salary Statement (ESS account) of May, 2017 is same as April, 2017. Pics attached for your reference. | SAP PAYROLL And HCM | Resolve
132 | 736 | 2017-06-10 17:34 | HIGH | Usha Menon Bose | Dear Team, The SAP ESS Account has been locked. Kindly generate a new password for login. | SAP ESS | Resolve
133 | 739 | 2017-06-12 13:25 | HIGH | SHAMSHAD UDDIN | In my Salary Statement (ESS account) of May, 2017 is same as April, 2017. Pics attached for your reference. | SAP ESS | Resolve
134 | 740 | 2017-06-12 13:42 | HIGH | SHAMSHAD UDDIN | I want to change my ESS Portal password. SAP ID - 20000133 | SAP ESS | Resolve
135 | 742 | 2017-06-12 17:01 | HIGH | Lavnish Goyal | Dear Team, When I try to fill Mileage details for reimbursement, attached message is displayed every time. I have tried filling data in all formats but still not able to rectify this error. Please do the needful | Not Assigned | Open
136 | 745 | 2017-06-13 15:25 | HIGH | MUKESH KUMAR RAY | I have submitted tour request from 19.5.2017 to 30.5.2017 but there is showing open request on EES Portal and also not submitted to Reporting boss | SAP ESS | Resolve
137 | 747 | 2017-06-13 19:01 | HIGH | K. Thirumurugan | Not able to login in employee self service and manager self service after login to essportal. Please see the attachment for your reference. | Not Assigned | New
138 | 754 | 2017-06-14 14:11 | HIGH | Neeraj Pal | Facing some issues while using ESS Portal, the details with screen shots are Uploaded for your reference and necessary action. | SAP ESS | Open
139 | 763 | 2017-06-14 17:29 | HIGH | NIKHIL BHANDARI | Kindly provide authorizations for create purchase order me21n on SAP. Authorization screenshot is attached herewith. | SAP PROJECTS | Close
140 | 770 | 2017-06-16 17:25 | HIGH | JISHA JYOTI | I am unable to download to the display form of my travel expense. Kindly help. | SAP ESS | Close
141 | 773 | 2017-06-19 11:44 | HIGH | Raj kumar Rakhra | Dear Team, I am facing issue in ESS/MSS portal. I receive mails saying that I have something to approve but when I login I do not get any items like tour requests, etc, to approve. My employee id is 10000084. | SAP ESS | Resolve
142 | 778 | 2017-06-20 10:27 | HIGH | RITIKA BHANDARI | While generating the payslip of off-cycle reimbursement, the Bank a/c is coming blank. Kindly incorporate the bank a/c details in payslip as it is shown in regular payroll payslips. | SAP ESS | Resolve
143 | 779 | 2017-06-20 10:44 | HIGH | Nitin Kumar Gupta | Dear Sir Similar to Advance to UPL , Kindly create one more special GL indicator for imp rest payment. So that we can avoid creating multiple imprest GL account in SAP. Appreciate if request can be taken on priority. | SAP FINANCE | Close
144 | 790 | 2017-06-21 15:20 | HIGH | DEEPAK KUMAR SAHANI | SAP FLM tab is not visible on my SAP ID | SAP FLM | Resolve
145 | 795 | 2017-06-22 13:35 | HIGH | Manoj Kumar Sangwal | Please correct my name to Manoj Kumar Sanwal | Not Assigned | New
146 | 797 | 2017-06-22 15:17 | HIGH | DHARMENDRA KUMAR SAHU | Login problem kindly reset the password Login ID:20000067 | Not Assigned | New
147 | 799 | 2017-06-22 18:38 | HIGH | NIKHIL BHANDARI | General Format of PO should be in Line with the LoA format as it was shared since the PO/LoA should be made in same lines. Please Find the attached sample PO for Your reference. | SAP PROJECTS | Assigned
148 | 801 | 2017-06-23 09:47 | HIGH | ARUN GUPTA | ESS Portal after a month ask for change the password. Its very difficult to remember the password which is changed every month . kindly do needful. | SAP ESS | InfoRequired
149 | 809 | 2017-06-23 16:18 | HIGH | Amod Kumar | Travel request raised by employ does not have From location due to which it is impossible to to book the ticket from the travel request. Hence we should get the clear instruction in Travel form below information Station from CLASS NEED TICKET Y/N REMARKS BY EMPLOYEE EMAIL ID OF EMPLOYEE APPROVED BY : CA(COMPETENT AUTHORITY) | SAP ESS | Open
150 | 813 | 2017-06-25 19:47 | HIGH | ARUN GUPTA | it was observed that some feature of the SAP Project is supported in the Macbook. Error shows that initialisation of Graphic is supported in SAP GUI. kindly check each feature of SAP Project in Macbook laptop and make all feature of SAP project compatible with Macbook laptop | SAP PROJECTS | Assigned
151 | 821 | 2017-06-28 16:02 | HIGH | ANIL AGRAWAL | Dear Team, I have been raising my claims for my mobile bill reibursement but the Claim is rejected due to unavailibilty of the uploaded file to the HR dept, I would request you to please take necessary action, Uploding the screen shot of my uploaded doc and also the screen shot of the HR dept where there is no visible file | SAP PAYROLL And HCM | InfoRequired
152 | 822 | 2017-06-28 19:26 | HIGH | S AMIT KUMARPRUSTY | Service Tax Return related all reports are pending | SAP FINANCE | Resolve
153 | 823 | 2017-06-28 19:33 | HIGH | Nitin Kumar Gupta | Dear Vivek / Ashish Based on the report provided, We are trying to reconcile the advance paid till now. But found that TM report show Rs 433378 as advance but GL show Rs 548175 as advance. Could you please check. | SAP PAYROLL And HCM | Forwarded
154 | 824 | 2017-06-28 19:35 | HIGH | Nitin Kumar Gupta | Dear sir Similar to Multipurpose advance , kindly create furniture advance as well in ESS portal. so, that we can adjust the furniture advance in payroll. | SAP PAYROLL And HCM | Assigned
155 | 825 | 2017-06-28 20:37 | HIGH | Nitin Kumar Gupta | Dear sir Kindly suggest how to include cashless medical payment of employee in employee IPD limit. | SAP PAYROLL And HCM | Open
156 | 826 | 2017-06-29 10:29 | HIGH | DEEPAK GARG | At the time of mobile reimbursement claim through SAP ESS portal, I am trying to select mobile reimbursement option but same is not coming. | SAP ESS | InfoRequired
157 | 843 | 2017-06-29 12:03 | HIGH | ARPIT GOEL | Kindly check the screen shot, I face problem at the time of payment process | SAP FINANCE | Open
158 | 852 | 2017-06-29 15:19 | HIGH | KUNAL SONI | The claim and reimbursement section.for the Id 10000166 has been locked, unable to log any claims. | SAP ESS | Open
159 | 859 | 2017-06-29 17:09 | HIGH | RAKESH KUMAR | i am not able to Log in SAP, kindly resolve at earliest | SAP FINANCE | Close
160 | 860 | 2017-06-29 17:11 | HIGH | RAKESH KUMAR | Dear Sir/Ma'sm, I am not able to Log IN in to SAP, kindly resolve this issue as on urgent basis. | SAP FINANCE | Resolve
161 | 866 | 2017-06-30 12:37 | HIGH | Markanda Charan Patra | I am not able to print my request. Please find attached the screen shot. Kindly do the needful. | SAP ESS | Resolve
162 | 868 | 2017-06-30 14:35 | HIGH | ANKUR GULATI | I'm not able to login to my SAP account with the last username & password. Kindly generate a new password. | SAP ESS | Resolve
163 | 871 | 2017-06-30 14:46 | HIGH | Sandeep Kumar | My tour request is not visible to my reporting manager on his SAP account. | Not Assigned | New
164 | 873 | 2017-07-03 10:35 | HIGH | Raj kumar Rakhra | Not able to take print out of any claims submitted in the portal. The error says "Error at the end of form processing and error while initiating travel form" | SAP ESS | Resolve
165 | 881 | 2017-07-03 19:16 | HIGH | DARPAN MAGO | SAP Travel Work Center not showing pending tours. Screenshot attached. This had happened earlier and now the problem has reoccurred. | SAP ESS | Resolve
166 | 889 | 2017-07-04 13:56 | MEDIUM | Ankit Rastogi | Unable to create leave request on ESS portal. Please resolve. | SAP ESS | InfoRequired
167 | 894 | 2017-07-05 10:18 | HIGH | RAHUL TIWARI | As discussed, May please create a wage type for Furniture Advance. Eligibility are as follows:- One Month Basic + DA as on date of application. Maximum Instalment would be 60 months excluding month of drawl of advance. As you said, creation of this wage type takes time, Due to this wage type, we are unable to recover the insalment in this month given to Johny Thomas on 11.05.2017. | SAP PAYROLL And HCM | Assigned
168 | 899 | 2017-07-05 12:53 | HIGH | ARUN GUPTA | It has been noticed that in the section of Claim & Reimbursement, Spectacles amount of Rs. 5000 is deducted form Max. of limit of basic salary and separate component is created. if some one doest need spectacles and his/her eyes are perfectly alright, in this case max. limit of OPD for particular employee may get reduce. kindly add the spectacle limit as secondary part of OPD and Create itself in OPD if required. | SAP ESS | Resolve
169 | 900 | 2017-07-05 14:31 | HIGH | NITIN BHATT | Hi, Unable to create request for medical claims. 'Create' feature not working. Request to please rectify. Regards, Nitin. | SAP ESS | Resolve
170 | 901 | 2017-07-05 15:22 | HIGH | RAHUL TIWARI | kindly change GL mapping of Stipend Apprentice and Stipend Payable. | SAP FINANCE | Resolve
171 | 902 | 2017-07-05 15:22 | HIGH | RAHUL TIWARI | kindly change GL mapping of Stipend Apprentice and Stipend Payable. | SAP FINANCE | Resolve
172 | 903 | 2017-07-05 15:22 | HIGH | RAHUL TIWARI | kindly change GL mapping of Stipend Apprentice and Stipend Payable. | SAP PAYROLL And HCM | Forwarded
173 | 904 | 2017-07-06 11:20 | HIGH | NIKHIL BHANDARI | Not Able to Download Note sheet from FLM. Please resolve it on Utmost Priority. | SAP ESS | Assigned
174 | 907 | 2017-07-07 14:40 | HIGH | AMAN MEHERDA | I am Aman Meherda id 10000100 please provide me SAP login password previous password is not working | SAP PROJECTS | Assigned
175 | 908 | 2017-07-07 14:45 | HIGH | SOUMYA PRASAD GARNAIK | I am raising my international travel claim for the first time and i am facing an issue regarding non calculation of DA amount and expenses amount. i am attaching screenshot for your reference. | SAP ESS | Resolve
176 | 911 | 2017-07-07 14:52 | HIGH | Markanda Charan Patra | 1. As per the rule, the OPD medical reimbursement limit should be Rs. 54,500/- for me. However it is mentioned as Rs. 49,500/- in the SAP portal. So, the same may corrected. 2.Further the balance amount under OPD medical reimbursement has been shown as 35,112/-. The details of my medical opd reimbursement credited to my account may be provided. | SAP PAYROLL And HCM | Forwarded
177 | 912 | 2017-07-07 14:52 | HIGH | Markanda Charan Patra | 1. As per the rule, the OPD medical reimbursement limit should be Rs. 54,500/- for me. However it is mentioned as Rs. 49,500/- in the SAP portal. So, the same may corrected. 2.Further the balance amount under OPD medical reimbursement has been shown as 35,112/-. The details of my medical opd reimbursement credited to my account may be provided. | Not Assigned | Close
178 | 917 | 2017-07-10 15:10 | HIGH | ARUN GUPTA | It is requested kindly change the service tax of 15% to GST 18% on ESS Portal for claim | SAP ESS | Assigned
179 | 923 | 2017-07-11 11:37 | HIGH | NEHA GERA | Dear All I am not able to view my form 16 in ESS portal. Kindly update. | Not Assigned | New
180 | 924 | 2017-07-11 11:38 | HIGH | ARPIT GOEL | At the time of confirmation of vendor through T Code FK08, I refuse some vendor due to wrong entry field, thereafter Initiator not able to edit again refuse vendors for entered correct data. | SAP FINANCE | Assigned
181 | 929 | 2017-07-11 12:30 | HIGH | PRASHANT KUMAR | In My SAP ESS portal did not create mail when i have create travel request. | SAP ESS | InfoRequired
182 | 931 | 2017-07-11 16:41 | HIGH | NANCY MEHTA | File notings are not in order as posted/ approved. | Not Assigned | Forwarded
183 | 932 | 2017-07-12 09:21 | HIGH | RAJNEESH RANA | While creating a travel request i am not able to provide a detailed plan for a journey as the Travel Preferences filed is missing/not visible. Screenshot attached. | SAP ESS | Close
184 | 934 | 2017-07-12 11:13 | HIGH | Nitin Kumar Gupta | One user have filled incorrect bank account in vendor master. Now system is not allowing to correct the same. | SAP FINANCE | Assigned
185 | 936 | 2017-07-12 12:00 | HIGH | Jitendra Kumar Koli | Please correct my name "Jitendra Kumar Koli" in ESSportal-EESL. | Not Assigned | New
186 | 948 | 2017-07-14 10:04 | HIGH | BHARAT KUMAR KANOJIYA | Email ID under MM modules are not updated. Upon creation of PR, did not received system generated email. May please look into this. | SAP PROJECTS | Assigned
187 | 949 | 2017-07-14 10:06 | HIGH | Lavnish Goyal | Dear Team, My ticket id 743 is still open. Please do the needful at the earliest. | SAP ESS | InfoRequired
188 | 951 | 2017-07-14 11:10 | HIGH | RAKESH KUMAR | Dear Sir/Ma;am, I am not able to Login into SAP, Please help immediately, i have to process payment through SAP | Not Assigned | New
189 | 964 | 2017-07-14 22:24 | HIGH | TOSH AGRAWAL | What is the meaning/full form of the enclosed text image in the Travel Request Form? Why it is not showing full text? | SAP ESS | Close
190 | 966 | 2017-07-15 13:36 | HIGH | RAHUL TIWARI | How to see no dues for an employee in case of relieving of Employee? | SAP FINANCE | Assigned
191 | 979 | 2017-07-17 11:59 | HIGH | PRAKASH JHA | attachment not opening | SAP ESS | InfoRequired
192 | 984 | 2017-07-17 12:39 | HIGH | VEDPRAKASH DINDORE | Corporate Street Lighting team moved note sheet through FLM to me but i am not getting authorization to respond on that. second i am also not able to see the note sheet. | SAP FLM | Resolve
193 | 985 | 2017-07-17 13:43 | HIGH | Karthikeyan A K | My travel request with the number 0010000425 is approved by Shri. Gopal Dayalani. But this request is not reflecting in the ESS portal - Traveler Workcenter | SAP ESS | Resolve
194 | 988 | 2017-07-17 16:20 | HIGH | TOSH AGRAWAL | How to cancel / modify an already approved tour? | SAP ESS | Close
195 | 989 | 2017-07-17 16:40 | HIGH | Neeraj Pal | Attendance is not showing in ESS Portal, whereas showing in savior. Please see attached file for reference. | SAP ESS | Assigned
196 | 990 | 2017-07-17 17:24 | HIGH | RAHUL TIWARI | Admin charges (EPF) for the month of June,2017 is not matching due to adjustment for previous year in current year. Kindly provide the solution. Also, Inspection charges has not been posted in G/L. Kindly look into this. | SAP PAYROLL And HCM | Resolve
197 | 991 | 2017-07-17 21:24 | HIGH | NITIN BHATT | Dear SAP Team, i have two EESL officer who is directly reporting to me. When they are submitting any tour approval and claim then i am unable to approved due to no any option coming in ESS portal to approve the same | Not Assigned | New
198 | 1001 | 2017-07-18 12:24 | HIGH | ARVIND SINGH BHANDARI | Dear Team, I am not able to login at http://essportal.eesl.co.in/irj/portal Kindly, reset it and provide a new password for the same. | Not Assigned | New
199 | 1002 | 2017-07-18 12:26 | HIGH | NANCY MEHTA | Leaves not reflecting correctly to the Approver. All the entries are redirecting to the same leave . Even after approving leave is not getting approved. | SAP ESS | Resolve
200 | 1003 | 2017-07-18 12:41 | HIGH | NAVEEN ANAND | Problem during SAP login in production. | SAP PROJECTS | Assigned
201 | 1004 | 2017-07-18 17:03 | HIGH | RAJNEESH RANA | After creating a travel request i tried to print the display request form and display expense form but both are not generating and showing an error. Screenshot attached. | SAP ESS | Resolve
202 | 1005 | 2017-07-18 18:29 | HIGH | K. Thirumurugan | Unable to generate Travel Expenses form | SAP ESS | InfoRequired
203 | 1012 | 2017-07-19 17:12 | HIGH | Nagsen Ambadas Wankhede | Why I am getting so many rows in Leave data overview ? I have not initiated this refer screen shot | SAP ESS | Resolve
204 | 1021 | 2017-07-24 12:43 | HIGH | Hemant Minz | Error code: 88...We are not able to log in. | SAP PROJECTS | Assigned
205 | 1022 | 2017-07-24 12:45 | HIGH | Nitin Kumar Gupta | In ESS portal, I am getting lot of Bonus payment salary slip with zero amount. Request you to kindly check the correct the same. | SAP PAYROLL And HCM | Assigned
206 | 1025 | 2017-07-24 18:20 | HIGH | SURLA V RAMA LOVA APPALA SWAMI NAIDU | I am trying to create a new note sheet in file management system in SAP portal. In my portal work is not work is not showing and also unable to select the same. | SAP FLM | InfoRequired
207 | 1027 | 2017-07-25 13:52 | HIGH | TOSH AGRAWAL | Dear Team The designation mentioned in the pay-slip shows only "Engineer (Technica" i.e. the last alphabets "l)" are cut. Kindly rectify the same. Furthermore, the bank account number shows twice in the salary slip, where in one of the mentioned account number, one digit is cut and is hence mismatching. Thank You | SAP PAYROLL And HCM | Assigned
208 | 1030 | 2017-07-25 14:26 | HIGH | Nitin Kumar Gupta | Dear sir How to see LOA wise payment tracking report in SAP. Please guide. Thanks | SAP FINANCE | Assigned
209 | 1032 | 2017-07-25 17:48 | HIGH | ARPIT GOEL | DA not calculate as per NTPC policy | SAP PAYROLL And HCM | Assigned
210 | 1033 | 2017-07-25 17:51 | HIGH | ARPIT GOEL | We are unable to calculate tour advance, In addition we unable to see tour advance for process | Not Assigned | New
211 | 1034 | 2017-07-25 17:51 | HIGH | ARPIT GOEL | how to adjust medical advance, if medical advance already given | Not Assigned | New
212 | 1035 | 2017-07-25 17:52 | HIGH | ARPIT GOEL | Bank reconciliation of all banks not process in SAP | Not Assigned | New
213 | 1036 | 2017-07-25 17:53 | HIGH | ARPIT GOEL | in payment advice should be shown related to which payment. | Not Assigned | New
214 | 1037 | 2017-07-25 17:59 | HIGH | ARPIT GOEL | SAP made payment of employee double. | SAP FINANCE | Assigned
215 | 1038 | 2017-07-25 18:00 | HIGH | ARPIT GOEL | At the time of file generation date format shown zero value | Not Assigned | New
216 | 1044 | 2017-07-26 11:12 | HIGH | RAHUL TIWARI | An IPD medical payment has been made to Amit Prusty (10000187) which is exempted, however, same is taxable and consider in Payroll. Kindly rectify the same. | SAP FINANCE | Assigned
217 | 1049 | 2017-07-26 13:09 | HIGH | RAHUL TIWARI | Kindly explain the reason for increase in Gross salary i.r.o Anil Agarwal (10000110) from June to July,2017. | SAP FINANCE | Assigned
218 | 1051 | 2017-07-26 14:07 | HIGH | Nitin Kumar Gupta | Dear sir Currently laptop / Mobile handset claim entry is coming as Exp. A/c Dr To employee a/c This entry is not correct as per accounting principle. Correct entry is Asset A/c Dr To Employee A/c Request you to kindly correct the same. | SAP FINANCE | Assigned
219 | 1063 | 2017-07-27 13:03 | HIGH | ARPIT GOEL | bank reverse file updated in SAP pending for reconciliation | SAP FINANCE | Assigned
220 | 1064 | 2017-07-27 13:06 | HIGH | RAHUL TIWARI | Individual Employee wise Tax Computation Sheet as per Salary Sheet share with Wipro Team. | SAP FINANCE | Assigned
221 | 1065 | 2017-07-27 13:06 | HIGH | RAHUL TIWARI | Individual Employee wise Tax Computation Sheet as per Salary Sheet share with Wipro Team. | Not Assigned | New
222 | 1066 | 2017-07-27 13:07 | HIGH | RAHUL TIWARI | Wrong HRA, PF, PF Arrear calculated by SAP which already been mail to Puneet Sir. | Not Assigned | New
223 | 1067 | 2017-07-27 13:08 | HIGH | RAHUL TIWARI | Lease discontinue ffrom this july however, still lease eligibility includes in HR. | Not Assigned | New
224 | 1069 | 2017-07-27 13:41 | HIGH | RAHUL TIWARI | Previous Employer Income as per Form 12B not available in SAP. | SAP FINANCE | Assigned
225 | 1070 | 2017-07-27 13:42 | HIGH | RAHUL TIWARI | Employee wise G/L Loan Balances not available in SAP. | Not Assigned | New
226 | 1071 | 2017-07-27 13:42 | HIGH | RAHUL TIWARI | In case of increment, Arrear on Cafeteria not calculated. | Not Assigned | New
227 | 1072 | 2017-07-27 13:43 | HIGH | RAHUL TIWARI | provision Of Foreign Salary not avilable in SAP | Not Assigned | New
228 | 1073 | 2017-07-27 13:44 | HIGH | RAHUL TIWARI | Revised DA incorporate manually. | Not Assigned | New
229 | 1074 | 2017-07-27 13:46 | HIGH | RAHUL TIWARI | if an employee shifts from FT to Regular, then what data need to be given to Firm for return. | Not Assigned | New
230 | 1075 | 2017-07-27 13:47 | HIGH | RAHUL TIWARI | How to control Loan and Balances given to employee through SAP. | Not Assigned | New
231 | 1076 | 2017-07-27 13:53 | HIGH | RAKESH KUMAR | Dear Sir/Ma'am, related to Swachh Bharat cess transaction, separate transaction stil pending | SAP FINANCE | Assigned
232 | 1077 | 2017-07-27 13:55 | HIGH | Nitin Kumar Gupta | Dear sir How to see Purchase register in SAP. Please guide. Thanks | SAP FINANCE | Assigned
233 | 1078 | 2017-07-27 13:55 | HIGH | RAKESH KUMAR | Dear Sir/ma'am, Mass uploading (JV) file still pending since two weeks | SAP FINANCE | Assigned
234 | 1079 | 2017-07-27 13:56 | HIGH | RAKESH KUMAR | Dear Sir/ma'am, Voucher printing is not properly | SAP FINANCE | Assigned
235 | 1080 | 2017-07-27 13:57 | HIGH | Nitin Kumar Gupta | Dear sir How to see summarized monthly comparison of Expenses in SAP. Please guide. Thanks | Not Assigned | New
236 | 1081 | 2017-07-27 13:59 | HIGH | RAKESH KUMAR | Dear Sir/Ma'am, Lease JV file still pending since Three weeks | SAP FINANCE | Assigned
237 | 1083 | 2017-07-27 15:19 | HIGH | RAKESH KUMAR | Dear Sir/Ma'am, i am not able to generate any report like vendors balance datewise, | SAP FINANCE | Assigned
238 | 1084 | 2017-07-27 15:19 | HIGH | RAKESH KUMAR | Dear Sir/Ma'am, i am not able to generate any report like vendors balance datewise, | SAP FINANCE | Assigned
239 | 1091 | 2017-07-28 12:58 | HIGH | SUDHA NAND ROY | Dear Sir/Madam, i am not able to login essportal, please help me for the same | Not Assigned | New
240 | 1093 | 2017-07-31 12:44 | HIGH | ANIL AGRAWAL | Dear Sir, I am unable to operate on My SaP installed in my Laptop, Request for your lookout in same Regards Anil | Not Assigned | New
241 | 1094 | 2017-07-31 13:16 | HIGH | Kavish Agarwal | In my ESS portal, I am unable to find the FLM system. Kindly do the needful at the earliest. | Not Assigned | New
242 | 1095 | 2017-07-31 14:04 | HIGH | SOUMYA PRASAD GARNAIK | Today i am entering my medical claim and an error message is coming as "Workflow not maintained for the Claim Type" Kindly rectify the issue. It has never happened in past. Screenshot is attached for your reference. | SAP ESS | Assigned
243 | 1098 | 2017-07-31 15:02 | HIGH | Abhishek Jain | I donot have access to SAP FLM system. The tab for FLM is not showing in ess portal. Kindly do the needful. | Not Assigned | New
244 | 1104 | 2017-08-01 11:37 | HIGH | Nitin Kumar Gupta | While raising HRA exemption request in SAP, system is not asking PAN number is Rent paid is above Rs100000. Request you to kindly correct. Thanks | SAP FINANCE | Assigned
245 | 1105 | 2017-08-01 12:36 | HIGH | RAHUL TIWARI | For Employee ID - 10000086 wherein two months Multi purpose advance recovery has been made fro salary, however, same is not mention in Payslip. And same is happen for all the employees for whom two months recovery have been made. kindly make available in Pay Slip also. | SAP FINANCE | Assigned
246 | 1106 | 2017-08-01 12:54 | HIGH | RAHUL TIWARI | once again recovery of Multi Purpose Advance (Employee ID-10000167) has been made from Payroll however, No such Multi purpose Loan has been credited to employee account, this was happened only due to non integration of module. kindly integrate this module. | Not Assigned | New
247 | 1108 | 2017-08-01 15:59 | HIGH | NITIN BHATT | While claiming of medical expenditure in SAP. under list of dependents my daughter's name is not being reflective. Request to please do the needful so I may claim a medical expense. Regards, Nitin Bhatt Manager, PR | SAP ESS | Assigned
248 | 1109 | 2017-08-01 16:28 | HIGH | RAKESH KUMAR | Dear Sir/Ma'am, i am not able to enter any entries related to Employees advance and taxi hiring charges, legal fee, sponsorship etc. Kindly help me immediately due to above said entries april 2017 backlog still pending. | SAP FINANCE | Assigned